Club Open Day - Example Action Plan
Please use and adapt these ideas to help with your club open day/taster session.
Pre-Open Day
	Week
	Actions
	Details
	Approximate date
	Who is responsible
	Completed (tick and date)

	
	The safety of the participants, coaches and volunteers is paramount, and the club and coach must conduct a risk assessment. 
	
	
	
	

	
	Have a club meeting to make members aware of the open day, reasons and to get their backing in creating a friendly welcoming environment. 
Also invite LA and Key Partners 
	
	
	
	

	
	Identify volunteers to help organise and run the Open day.
	
	
	
	

	
	Identify membership area you would like to target. General beginners, families, women and girls etc.
	
	
	
	

	
	Agree a ‘trial membership’ package with committee for beginner scheme attendees. Look at current membership offers and see if they suit differing lifestyle and needs
	
	
	
	

	
	Arrange date for Open Day/Taster session
	
	
	
	

	
	Organise a remote meeting with key volunteers:

· Distribute roles

· Discuss ideas on how and where to promote Open day/taster session
	
	
	
	

	
	Develop a communication plan this may include ideas such as:

· Emailing membership - encourage them to promote with family and friends

· Social media (77% of women use face book)

· Posters, distribute in local shops, businesses, residential areas, other sports clubs etc.

· Press editorial

Think about what local facilities you have access to? 

What companies do your members work for? Can they promote in their workplace?

Local sports clubs? 

Member friend and family? 

Taster sessions in schools and community clubs to promote free taster day?

Town centre campaign?

Local fete? Etc.
	
	
	
	

	
	Plan your Open day/session.
Contingency - organise what will happen in adverse weather conditions. (Adhering to government restrictions).
	
	
	
	

	
	Ensure telephone/ email booking sheets are placed by telephone/ computer and people answering is fully aware of Open Day/session
REMEMBER – when participant’s book encourage them to bring a friend or family member if they wish.
	
	
	
	

	
	Ensure all current members are aware that the Open Day/session is taking place and that there will be a relaxed dress code for all beginners on the scheme
	
	
	
	

	
	Design a promotional letter and email detailing continuation of sessions and trial membership (outline the benefits) 
	
	
	
	

	
	Design a promotional letter/flyer for full membership (outline the benefits)
	
	
	
	


During the Event
	Week
	Actions
	Details
	By when
	Who is responsible
	Completed (tick and date)

	
	Turn up 2 hrs prior to start to set up 

	
	
	
	

	
	Meet and greet participants in the car park or clearly display signs

	
	
	
	

	
	Make sure participants emails/contact numbers are gathered on registration for future communication.

	
	
	
	

	
	Encourage the participants to use the club house during and after the event for refreshments to increase the social element.

	
	
	
	

	
	Throughout scheme 

· talk about next offer. E.g. additional taster sessions and trial membership, along with the benefits.

· Promote the next session/event
	
	
	
	


Post Scheme

	
	Actions
	Details
	By when
	Who is responsible
	Completed (tick and date)

	
	Promote membership options

· talk about next offer. E.g. additional taster sessions and trial membership, along with the benefits.

· Send regular reminders about the next session
	
	
	
	

	
	Encourage participants to play with current members

	
	
	
	

	
	Organise fun competitions or weekly roll ups

	
	
	
	

	
	Promote and arrange social activities

	
	
	
	

	
	Encourage them to invite family and friends to the club and potentially to have ago themselves
	
	
	
	


If you have any questions, please do not hesitate to contact us.

[image: image1.jpg]Fay
2

S 4550



[image: image2.png]Welsh Bowling Association

&8



[image: image3.png]CROWp
hos



[image: image4.png]


[image: image5.png]


[image: image6.png]“%” Welsh Women’s

Bowling Association



[image: image7.png]


[image: image8.jpg]BowlsCymru
BowlsWales



 
